# Orthotics Referral Pathway Evaluation Report – Updated for 2024 and 2025

# Evaluation and Optimisation of Orthotics Referral Pathway

Community Rehab Team North
Marc Riley
2025/2026

# 1. Project Initiation Document (PID)

## Title

Evaluation and Optimisation of Orthotics Referral Pathway

## Background

Within the Community Rehabilitation Teams (CRT) North and South Trafford, referrals to the Orthotics Service were historically made indirectly via General Practitioners (GPs). This required clinicians to write to the patient’s GP, who then forwarded the referral to the Orthotics Service. Anecdotal feedback suggested this introduced delays, duplication of administrative work, and potential loss or alteration of clinical information.

The expanded 2024 dataset confirms these concerns, showing variable delays between CRT request and GP forwarding, inconsistent data quality, and limited transparency across the pathway.

## Problem Statement

- Indirect referral pathway via GPs

- Potential delays between stages

- Risk of lost or incomplete information

- Increased administrative burden

- Uncertainty around demand for commonly used orthotics

- Uncertainty around volume of referrals made by CRT to orthotics

## Aim

To evaluate the efficiency of the current orthotics referral pathway and identify opportunities to improve timeliness, reduce unnecessary steps, and enhance patient experience.

## Objectives

- Quantify referral activity over 6 months

- Measure time intervals across the pathway

- Identify delays and inefficiencies

- Assess feasibility of direct referral

- Evaluate demand for common orthotics

- Explore feasibility of stockholding

## Scope

In Scope: CRT North & South referral processes, GP and Orthotics interface, referral timelines, common orthotic usage.
Out of Scope: Full financial modelling, clinical outcomes post-provision, post-assessment timelines.

# 2. Business Case

## Overview

This project explores two workstreams:

- Referral pathway optimisation

- Feasibility of orthotics stockholding

## Current Situation (2024)

CRT referrals were made via GPs. The expanded 2024 dataset (20 referrals) shows:

- Average GP → Orthotics delay: 10.6 working days

- Average Orthotics receipt → Initial Assessment: 33 working days

- Average total pathway: 42.5 working days

- No GP rejections recorded

- Several data quality issues across systems

## Case for Change

- Reduce delays in patient care

- Improve efficiency of referral process

- Reduce administrative burden

- Improve information transfer

- Enhance patient experience

## Options

- Maintain current pathway - no change, continued inefficiencies

- Direct referral to Orthotics - reduced delays, improved communication

- Introduce stockholding - faster access to simple devices

- Combined approach - maximum efficiency, more complex to implement

## Benefits

- Faster patient access

- Reduced workload

- Improved pathway efficiency

- Potential reduction in inappropriate referrals

# 3. Stakeholder Analysis

Stakeholders: GPs, CRT clinicians & leadership, Orthotics Service, Procurement, Admin teams, Patients.

Power/Interest Grid:

- High Power / High Interest: Orthotics Service, CRT Leadership

- High Power / Low Interest: GPs, Procurement

- Low Power / High Interest: CRT Clinicians, Patients

- Low Power / Low Interest: Wider admin teams

Considerations:
GPs may resist removal from pathway; Orthotics capacity must be considered; Procurement involvement required for stock.

# 4. Communication Plan

| Stakeholder | Information | Method | Frequency |
| --- | --- | --- | --- |
| CRT Team | Progress updates | Meetings/email | As required |
| Orthotics Service | Process discussions | Meetings | As required |
| GPs | Proposed changes | Formal communication | Once agreed |
| Leadership | Project outcomes | Reports/presentations | Key stages |

# 5. Process Mapping

## Current Process (2024)

CRT → GP → Orthotics → Appointment

Issues Identified:
Delays, duplication, lack of transparency.

## Proposed Process

CRT → Orthotics → Appointment

# 6. Data Collection & Methodology

- Retrospective review over 6 months (June-December 2024)

- Data from CRT records and Orthotics Service

- Data analysed using Excel

- Informal staff consultation

- Stakeholder engagement with Orthotics Service

# 7. Data Analysis & Findings (2024)

## Overview of Dataset

The expanded dataset includes 20 referrals for 2024. This maintains the original pattern of steady but modest referral activity.

## Referral Activity

Referral activity remained consistent month-to-month, confirming the original finding that perceived referral volume was higher than actual activity.

## Pathway Timings

- Average GP → Orthotics: 10.6 days

- Average Orthotics → IA: 33 days

- Average Total Pathway: 42.5 working days

These results show that the GP forwarding stage contributed an average 10.6 working days to the pathway. The findings supported testing a direct-referral model that removed this handoff.

## Delays Within the Pathway

The GP forwarding stage added an average 10.6 working days before receipt by Orthotics. No referrals were rejected in the 2024 dataset, supporting review of whether this handoff was necessary within the pathway.

## Data Quality and Process Visibility

The expanded dataset confirms:

- Inconsistent sequencing of referral stages

- Manual data gathering across systems

- Occasional missing or incorrect data

- Duplicate NHS numbers

- Variation in terminology and coding

These issues reinforce the need for a simplified, direct referral pathway.

## Orthotic Demand Patterns

Demand remained consistent with the original findings:

- Shoe raises: 6 referrals

- Orthotic - Foot: 5 referrals

- Orthotic - Knee: 4 referrals

- Footwear: 2 referrals

- Orthotic - Arm/Wrist: 2 referrals

Only one referral aligned with potential stock items, confirming that stockholding is not justified.

## Summary of Findings (2024)

- Prolonged pathway due to GP involvement

- Inconsistent data tracking

- Recurrent demand for common orthotics

- No evidence supporting stockholding

- Variation in patient experience and waiting times

# 8. 2025 Findings - Direct Referral Model

In 2025, CRT implemented direct referral to Orthotics, removing GP involvement entirely. The dataset includes 23 referrals.

## Key Improvements

- GP → Orthotics delay reduced to 0 days

- Average Orthotics → IA: 35 working days (33 working days in 2024)

- Average total pathway reduced from 42.5 to 35 working days (17.6%)

- Improved data quality due to fewer handoffs

## Referral Activity

Referral volume increased slightly from 20 to 23 referrals. The dataset does not establish the reason for this change.

## Orthotic Demand Patterns (2025)

Demand remained similar:

- Shoe raises: 7 referrals

- Orthotic - Foot: 7 referrals

- Orthotic - Knee: 4 referrals

- Footwear: 3 referrals

- Orthotic - Arm/Wrist: 2 referrals

This consistency supports the reliability of the dataset.

## Summary of Findings (2025)

- Direct referral eliminated the largest source of delay

- Pathway became more predictable

- No inappropriate referrals recorded

- Clinicians reported smoother workflow (informal feedback)

# 9. Comparison: 2024 vs 2025

| Measure | 2024 | 2025 | Change |
| --- | --- | --- | --- |
| Referral volume | 20 | 23 | ↑ 3 referrals |
| GP → Orthotics delay | 10.6 days | 0 days | Removed |
| Orthotics → IA | 33 days | 35 days | ↑ 2 days |
| Total pathway | 42.5 days | 35 days | ↓ 17.6% |
| Data quality issues | Several | Fewer | Improved |
| Stockholding need | Not supported | Not supported | No change |

## Interpretation

Following introduction of direct referral, average total pathway time reduced from 42.5 to 35 working days (17.6%). The removed GP referral stage had previously accounted for an average 10.6-working-day delay. Orthotics-to-initial-assessment time did not improve, increasing slightly from 33 to 35 working days, suggesting that the observed reduction in total pathway time was associated with removal of the GP handoff rather than improved downstream waiting times. No referrals were rejected in either dataset.

This is a small, service-level descriptive evaluation (20 referrals in 2024 and 23 in 2025). The findings show an observed association between introduction of direct referral and shorter overall pathway time; they do not constitute formal causal proof. Clinical outcomes after orthotic provision and full financial modelling were outside scope.

Observed total-pathway range narrowed from 26-50 working days in 2024 (range width 24 days) to 28-40 working days in 2025 (range width 12 days), a 50% reduction in observed range width.

# 10. Conclusion & Recommendations

## Conclusion

The evaluation found a shorter overall referral pathway following removal of the GP handoff. Average total pathway time reduced from 42.5 working days in 2024 to 35 working days in 2025 (17.6%), while the average Orthotics-to-initial-assessment interval increased slightly from 33 to 35 working days. The observed pathway range narrowed from 26-50 to 28-40 working days. No referrals were rejected in either dataset. These descriptive findings support continuation of the direct-referral model alongside ongoing monitoring of downstream waiting times and data quality.

## Recommendations

- Adopt direct referral pathway permanently

- Improve pathway visibility and data recording

- Do not pursue stockholding

- Continue monitoring referral activity and waiting times

- Develop standardised referral documentation

# Appendix

- Dataset (2024 and 2025)

- Proposed referral template

- Dashboard outputs (2024)